## Sheet1
| Completed |  | On-going |  | Planned |  | NEED PARTNER |  |  |  | TBC
Date
| Location |  |  |  |  | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Completed
Status | Province | District | Sub-District | Locations needed | Organisation | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | On-going
Province A | [21 empty] | planned
Completed | A | Omega | OA |  | Partners 1,2 and 3 | [16 empty] | TBC | bar: Date Sun 31
Completed | A | Delta | DA | 4-5 | Partners 1+2 | [16 empty] | NEED PARTNER | bar: Date Tue 2 to Date Wed 3
Completed | A | Delta | DE | 4-5 | Partners 1+3 | bar: Date Tue 2 to Date Wed 3
Completed | A | Delta | DE | 4-5 | Partners 1+4 | bar: Date Tue 2 to Date Wed 3
On-going | A | Beta | BA | 4-5 | Partner 4 | bar: Date Tue 2 to Date Fri 5
planned - Additional needed - SAVE TBC | A | Beta | BA | 4-5 | planned - Additional needed - SAVE TBC | bar: Date Sun 7
NEED PARTNER | A | Foxtrot | FA | 4-5 | NEED PARTNER
NEED PARTNER | A | Foxtrot | FG | 4-5 | NEED PARTNER
planned | A | Foxtrot | FG | 4-5 | Partner 4 | bar: Date Mon 8
Partner Z | A | Foxtrot | FG | 4-5 | Partner 5 | bar: Date Tue 9 to Date Thu 11
planned | A | Bravo | BT | 4-5 | Partners 5/6 | bar: Date Wed 10 to Date Fri 12
planned | A | Bravo | BT | 4-5 | Partners 5/7 | bar: Date Wed 10 to Date Fri 12
planned | A | Bravo | BX | 4-5 | Partners 5/8 | bar: Date Wed 10 to Date Fri 12
TBC - Partner D | A | Tango | TA | 4-5 | Partner 10
planned | A | Tango | TM | 4-5 | Partner 10 | Date Tue 9: TBC
Province B
On-going | B | Echo | EA | 4-5 | Partner 7 ADDITIONAL NEEDED!! | bar: Date Thu 4 to Date Mon 15
planned | B | Echo | EA | 4-5 | 4+5 | bar: Date Tue 9 to Date Mon 15
On-going | B | Echo | EM | 4-5 | 4+5 | bar: Date Sat 6 to Date Sun 7
planned | B | Echo | EG | 4-5 | 1/2/3 ADDITIONAL NEEDED!! | bar: Date Tue 9 to Date Mon 15
planned | B | India | IZ | 4-5 | Partner 11 | bar: Date Tue 9 to Date Fri 12
planned | B | India | IM | 4-5 | Partner 12 | bar: Date Tue 9 to Date Fri 12
On-going | B | India | II | 4-5 | Partner 13 | bar: Date Sat 6 to Date Fri 12
On-going | B | India | IF | 4-5 | Partner 14 | bar: Date Fri 5 to Date Fri 12

## filled
Site coverage - May and June 2022
Date
Location |  | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Province | Site | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | 1 | Date Sun 31: Yes
2
| 3 | Date Tue 2: Yes; Date Wed 3: Yes
| 4 | Date Tue 2: Yes
| 5 | Date Thu 4: Yes; Date Fri 5: Yes; Date Sat 6: Yes; Date Sun 7: Yes; Date Mon 8: Yes; Date Wed 10: Yes; Date Thu 11: Yes; Date Fri 12: Yes
6
| 7 | Date Mon 1: Yes; Date Wed 3: Yes; Date Fri 5: Yes; Date Sun 7: Yes
B | 8 | Date Sun 31: Yes
9
| 10 | Date Tue 2: Yes
| 11 | Date Tue 2: Yes
| 12 | Date Thu 4: Yes; Date Wed 10: Yes
13
| 14 | Date Mon 1: Yes; Date Wed 3: Yes; Date Fri 5: Yes; Date Sun 7: Yes

## site_coverage_merged
Site coverage - May and June 2022
Date
Location |  | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Province | Site | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | 1 | Date Sun 31: Yes
2
| 3 | Date Tue 2: Yes
| 4 | Date Tue 2: Yes
| 5 | Date Thu 4: Yes; Date Wed 10: Yes
6
| 7 | Date Mon 1: Yes; Date Wed 3: Yes; Date Fri 5: Yes; Date Sun 7: Yes
B | 8 | Date Sun 31: Yes
9
| 10 | Date Tue 2: Yes; Date Sat 6: Yes
| 11 | Date Tue 2: Yes; Date Thu 4: Yes
| 12 | Date Thu 4: Yes; Date Wed 10: Yes
13
| 14 | Date Mon 1: Yes; Date Wed 3: Yes; Date Fri 5: Yes; Date Sun 7: Yes

## Tidy
Date | Province | Site | Status
2022-05-31 | A | 1 | Yes
2022-06-02 | A | 3 | Yes
2022-06-03 | A | 3 | Yes
2022-06-02 | A | 4 | Yes
2022-06-04 | A | 5 | Yes
2022-06-05 | A | 5 | Yes
2022-06-06 | A | 5 | Yes
2022-06-07 | A | 5 | Yes
2022-06-08 | A | 5 | Yes
2022-06-10 | A | 5 | Yes
2022-06-11 | A | 5 | Yes
2022-06-12 | A | 5 | Yes
2022-06-01 | A | 7 | Yes
2022-06-03 | A | 7 | Yes
2022-06-05 | A | 7 | Yes
2022-06-07 | A | 7 | Yes
2022-05-31 | B | 8 | Yes
2022-06-02 | B | 10 | Yes
2022-06-03 | B | 10 | Yes
2022-06-06 | B | 10 | Yes
2022-06-07 | B | 10 | Yes
2022-06-02 | B | 11 | Yes
2022-06-04 | B | 11 | Yes
2022-06-04 | B | 12 | Yes
2022-06-05 | B | 12 | Yes
2022-06-06 | B | 12 | Yes
2022-06-07 | B | 12 | Yes
2022-06-08 | B | 12 | Yes
2022-06-10 | B | 12 | Yes
2022-06-11 | B | 12 | Yes
2022-06-12 | B | 12 | Yes
2022-06-01 | B | 14 | Yes
2022-06-03 | B | 14 | Yes
2022-06-05 | B | 14 | Yes
2022-06-07 | B | 14 | Yes